## WBS
Social Media App Development
Deliverables | Description | Estimated Man Hours
|  | Development | QC/Testing | Project Management | TOTAL
I) Native iOS (iphone) Application for End-Users | 1.Business Analysis & Communication | 8 |  | 0.8 | 8.8
| 2. Base Code & Architecture | 4 | 0.6 | 0.4 | 5
3. User Features:
| 3.1 Splash Screen > When the end user will open the application, an attractive splash screen along with the logo of the application will appear. | 0 | 0 | 0 | 0
| 3.2 Sign In/ Login Screen > If user is already registered within the app and logged out from own account or downloaded the app in new device, then the user can login to his/ her own account within the application by providing the following information: i ) Email-Address/ Mobile Number/ Username ii ) Password > If the above data provided by the user are correct, the application will be redirected at the “Home Screen”. >Other options available over this screen are as follows: Forgot Password: There will be a ‘Forgot Password’ option at this screen, which will redirect the end user at the 'Forgot Password Screen'. Sign Up: The new users can create account from here in the application. Users will be redirected to 'Sign Up' Screen. | 4 | 0.6 | 0.4 | 5
| 3.3 Forgot Password Screen > Through this screen, the end user will be able to retrieve their password in case if they forgot. For that, they have to mention their registered email address/ mobile number at this screen. > A link will be sent to the registered email address/ mobile number for setting the password. | 2 | 0.3 | 0.2 | 2.5
| 3.4 Sign Up Screen > If end user is not an existing user, then end user will be able to create new account by providing the following details: o Name of the end user(First Name & Last Name)*// mandatory fields o Unique Username* o Mobile Number* o Email Address* o DOB* o Gender * o Password* o Confirm Password* > The user can skip the below details for creating an account. o Profile Image o Short Bio o Status (Example: Married, Single) o Designation (From: Drop Down) o Address o Option: Register* > User will be able to view Terms and Conditions and Privacy Policy by clicking on it, through this screen. > User will have to fill the * marked options and rest details can be skipped for registration process. | 8 | 1.2 | 0.8 | 10
| 3.4.1 OTP Verification Screen > This screen would enable the end users to receive the 4 digits OTP over their registered mobile number/ Email ID. > The user would need to mention the OTP code at this screen for the purpose of Verification within limited seconds. > There would be a 'Resend OTP' option also available for the end users to opt for it. > Once user mentioned the OTP and is verified successfully, the user will be redirected to the “Home Screen”. | 4 | 0.6 | 0.4 | 5
| 3.5 Home Screen (My Timeline) > The end users would be redirected over this screen once they have successfully registered/ logged into the application. - Feed > User can view post of other end users (Followers & Following) as well as their own post. o Profile Image o Username o Post (Images or Video) o Number of Likes on Post (user can also give like to post) o Number of Comments on Post (user can also add comment) o Share (User can share the post to other end-users within the application) o Add To Favourites > Ellipsis o View profile o Block o Unfollow o Report o Hide Post o Turn on notifications for post > There will be search panel,Chat and Stories on the top of screen o Search Panel: On clicking here, user will be redirected to 'Search' Screen. o Chat: On clicking here, user will be redirected to 'Chat Listing' Screen. There will be count of unread messages. o Stories: User will be able to 'Add Story' or have 'Live Streaming' and can also view story of other end users from here. o Profile Icon: On clicking here, user will be redirected to 'Profile Details' Screen. - Bottom Bar: o Home: On clicking here, user will be redirected to 'Home' Screen. o My Activity: On clicking here, user will be redirected to 'My Activity' Screen. o Explore: On clicking here, user will be redirected to 'Explore' Screen. o Add Post: On clicking here, user will be redirected to 'Add Post' Screen. o Account Settings: On clicking here, user will be redirected to 'Account Settings' Screen. > When the user is a new user then they will have suggestions in feed on basis of location, Contacts, Public Profiles, Most Followed Profiles and verified profiles. > On clicking at username in post from the feed, user will be redirected to that user's profile. > User needs to grant permission for Location Access, Gallery, Media, Camera, Sync Contacts and Notifications for the application. | 38 | 5.7 | 3.8 | 47.5
| 3.6 Search Screen > Users will be redirected here by clicking on search panel from the home screen. > Users will be able to search for profiles by username, name or keyword. | 8 | 1.2 | 0.8 | 10
| 3.7 Explore Screen > Users can be able to view all published posts (Images or Videos) by all the public accounts. > On clicking at any post from the timeline, user will be able to view the post details just like the post details of feed. | 8 | 1.2 | 0.8 | 10
| 3.8 Other User's Profile > The users can be redirected here on clicking at profile image from post, request, view profile from the chat or from search history. o Profile Image o Username o Count of their friends (On clicking here, user will have a list of all their friends. On clicking at any friend, user will be redirected to that friend's profile) o Post Uploaded (User can view, give like, add comment, share and save to favourites) o View Details (Example: Bio, Status) o Options: - Send Follow Request - Accept Request (If Requested) o Ellipsis - Hide/ Unhide Story - Share Profile > User can only view the post/s and friend list if the account is open or already following the end-user. Rest the end-user can only view the count of friends and post and send request. | 8 | 1.2 | 0.8 | 10
| 3.8.1 Send Message | 8 | 1.2 | 0.8 | 10
| 3.8.2 Block User | 8 | 1.2 | 0.8 | 10
| 3.8.3 Report User | 8 | 1.2 | 0.8 | 10
| 3.9 My Activity > User will be able to view request from other users to follow them and accept their friend request. > Users will have count of all pending request. o Profile Image o Username - Options: o Accept o Follow Back o Delete > On clicking at username, user will be redirected to profile of that user. > User can view the likes and comments on their post by friends from here. > User can view all the notifications from here. | 8 | 1.2 | 0.8 | 10
| 3.10 Add Post - Option: Add New o User can add images or videos (Up to 5) and add a caption to post. > User can apply Filter to each image like cropping, brightness, contrast, some basic filters. The video should be of less than 60 seconds. There will be no filters applicable to video. > User can view comments and likes on previous post. User can delete any comment from the post. - Note: The comments will be nested to single layer only. | 24 | 3.6 | 2.4 | 30
| 3.11 Profile Details Screen o Profile Icon o Username o Number of Followers: On clicking here, user will have list of followers with profile image and username. User can remove them followers and can also view their profile. o Number of Following: On clicking here, user will have list of following with profile image and username. User can remove them following and can also view their profile. o Number of Post: User can view all the previously added post to their profile. They can edit the post and view all the comments and likes on post | 16 | 2.4 | 1.6 | 20
| 3.12 Add Story - Option: Add Story > User will be able to add story to their profile from here. > User can upload image or video to story from device storage or by clicking a camera image or record a video. > User can apply basic filters to the story. > The story will be visible for next 24 hours in their profile. | 16 | 2.4 | 1.6 | 20
| 3.12.1 Live Streaming > User will be able to have a live streaming for their friends from here. The host will be able to share video and view the connected users. > The friends (Other users) can only view video. > The user can upload that live streaming as story in their profile which will be visible for next 24 Hours. | 20 | 3 | 2 | 25
| 3.13 Chat Listing Screen > User will be able to view all the previously initiated chat here. The recent chats will be on top. > There will be a count of unread messages for each chat. - Option: Make Group (User will be able to Add Other Users and give Name to that group and set group image). o Profile Image o Username/ Groupname o Last Message > The chat will be stored locally. | 12 | 1.8 | 1.2 | 15
| 3.13.1 Chat Detail Screen o Profile Image o Username o Ellipsis - View profile - View shared media - Delete Chat - Mute Chat - Block Profile - Report Profile o Conversation Messages o Options: - Enter Text (Text message) - Record Audio/Video - Capture Image - Send Documents (Images, Videos, PDF Files) | 12 | 1.8 | 1.2 | 15
| 3.13.1.1 Audio/ Video Call | 8 | 1.2 | 0.8 | 10
| 3.14 Account Settings > User will be redirected here from the Home Screen. o My Profile: On clicking here, user will be redirected to 'My Profile' Screen. o My Post: On clicking here, user will be redirected to 'My Post' Screen. o My Favourites: On clicking here, user will be redirected to 'My Favourites' Screen. o Profile Settings: On clicking here, user will be redirected to 'Profile Settings' Screen. o Help & Support: On clicking here, user will be redirected to 'Help & Support' Screen. o Contact Us: On clicking here, user will be redirected to 'Contact Us' Screen. o Delete Account o Deactivate Account o Log Out | 8 | 1.2 | 0.8 | 10
| 3.14.1 My Profile > User will be able to view and edit changes of their profile from here. - Option: Edit Profile o Name of the end user o Unique Username o Mobile Number o Email Address o Profile Image o Short Bio o DOB o Gender o Status (Example: Single, Married) o Designation (Example: Student, Business) o Address o Option: Change Password | 8 | 1.2 | 0.8 | 10
| 3.14.2 My Favourites > User can view all the favourite marked post/s from here in a list view. On clicking at post from list view, user can have details of that post. - Options: Remove from Favourites | 8 | 1.2 | 0.8 | 10
| 3.14.3 Profile Settings - Options: o Privacy Settings o Story Settings o Blocked Accounts | 6 | 0.9 | 0.6 | 7.5
| 3.14.3.1 Privacy Settings > User can mark their profile as private or public from here. | 4 | 0.6 | 0.4 | 5
| 3.14.3.2 Story Settings > User can mark to whom their story should be visible. User can also hide profiles from here to which their story will not be visible. o Only Followers o Both (Followers & Following) | 4 | 0.6 | 0.4 | 5
| 3.14.3.3 Blocked Accounts > User can view all the blocked accounts from here in a list view. - Option: Unblock | 6 | 0.9 | 0.6 | 7.5
| 3.14.4 Static Content Screens > User can view the below static content from here. o FAQs o Privacy Policy o Terms & Conditions | 4 | 0.6 | 0.4 | 5
| 3.14.5 Contact Us (* Native Mail Composer) > User can send a feedback or query to Admin from here. | 4 | 0.6 | 0.4 | 5
Other Integrations:
| 1. Chat Integration API Integration: Quickblox Integration | 16 | 2.4 | 1.6 | 20
| 2. Live Streaming API Integration: AWS Integration | 20 | 3 | 2 | 25
| 3. Push Notification Integration | 2 | 0.3 | 0.2 | 2.5
| 4. For Image/Video Editing: For iOS: CI Filter For Android: GPU Image | 20 | 3 | 2 | 25
| Subtotal: | 342 | 50 | 34 | 426
II) Native Android (Smartphone) Application for End- Users | Subtotal: | 342 | 50 | 34 | 426
III) Design (UI/UX Graphic Designing) | Subtotal: | 50
IV) Web Based Admin Dashboard | 1. Business Analysis & Communication | 8 |  | 0.8 | 8.8
| 2. Database Creation | 8 | 1.2 | 0.8 | 10
| 3. Web Services | 70 | 10.5 | 7 | 87.5
4. Admin Panel Features:
| 4.1 Admin Login (Username & Password) | 2 | 0.3 | 0.2 | 2.5
| 4.2 Forgot Password | 1 | 0.15 | 0.1 | 1.25
| 4.3 Dashboard > It would have various analytics for the System Admin to review the smooth flow over the platform. o Active Users o Most Followed Users o Most Liked Post o Most Commented Post | 8 | 1.2 | 0.8 | 10
| 4.4 Manage Users (View, Add, Edit, Delete, Activate/ Deactivate) | 8 | 1.2 | 0.8 | 10
| 4.5 Manage Post (View, Edit, Delete, Search by Username) | 8 | 1.2 | 0.8 | 10
| 4.6 Manage Reported Post (View, Edit, Delete) | 8 | 1.2 | 0.8 | 10
| 4.7 Manage Custom Push Notifications | 8 | 1.2 | 0.8 | 10
| 4.8 Manage Designation List (Add, View, Edit, Delete) | 8 | 1.2 | 0.8 | 10
| 4.9 Account Settings - Change Username - Change Password option | 4 | 0.6 | 0.4 | 5
| 4.10 Log Out | 0 | 0 | 0 | 0
Other Integration:
| Twilio SMS Gateway | 4 | 0.6 | 0.4 | 5
| Subtotal: | 145 | 21 | 15 | 180